## Instructions
State Entity RFx Project Plan
State of Georgia Department of Administrative Services
Instructions for Issuing Officer
The RFx Project Plan has been developed as a Procurement Tool to assist Issuing Officers and Program Owners in mapping out the required tasks, resources, deliverables, and timelines necessary to meet their Implementation Date. The initial Project Plan is developed by the Issuing Officer and then confirmed with the Key Stakeholders. The Project Plan is annotated as you move through the solicitation process and is aligned to the Seven Stages of Procurement. As each Stage is completed, a revised Project Plan based on the actual completion dates may be needed. The Issuing Officer will use the Comments field to capture variances in the Project Timeline for both documentation and lessons learned. The initial stages of the Project relate to any sourcing project - RFI, RFQ, RFQC, or RFP. The Project Plan has specific directions by Stage as to whether you would continue with the Project Plan or close the Project Plan based on a sourcing decision.
1. Enable content (if prompted). 2. Review applicable stage and processes. 3. Review, add and delete tasks, as applicable. 4. Assign resources and dates to tasks. 5. Document expectations, risks and adjustments made in "Comments" field. 6. Track progress and adjust dates as stages are completed.
Revised 07/01/2026 SPD-PS023

## State Entity RFx Project Plan
[INSERT PROJECT NAME]
| Organization Name: |  |  |  |  | Start Date
Issuing Officer Name:
Solicitation Type:
| Solicitation ID: |  |  |  |  | Completion Date
Project Sponsor and Key Team Members:
Task No. | Task | Purpose | Resource Assigned | Status | Scheduled Date | Actual Date Completed | Deliverables | Comments
NI1 | Plan and schedule a fact-finding meeting with identified end user(s) who initiated request. Complete SPD-NI001 Fact Finding Agenda. The purpose of this meeting (or series of meetings) is to under the need, who needs it, why it is needed, when it is needed, who needs to be involved, etc. |  | Issuing Officer |  |  |  | Meeting Date
NI2 | Conduct the fact-finding meeting with the end user(s). Use SPD-NI001 Fact Finding Agenda and other materials provided by requester to drive fact-finding meeting. |  | Issuing Officer |  |  |  | Completed Meeting Agenda (SPD-NI001) and high-level project information.
NI3 | Initiate the data collection process. It may be beneficial to conduct a survey to further understand the need. |  | Issuing Officer |  |  |  | Survey Document
NI4 | Develop profiles on specific category opportunities (category, supplier, spend reports, etc. enable visibility for the issuing officer). |  | Issuing Officer
NI5 | Document fact-finding meeting notes and distribute. Request feedback to ensure that you captured the need and the end user(s) agree with your understanding of what is needed. |  | Issuing Officer |  |  |  | Fact-finding meeting minutes - Documented needs
NI6 | Determine if there is a need for purchase or establishment of a new contract. - Use input from the fact-finding meeting - Analyze existing contract sources and apply the Order of Precedence. - Determine whether a sourcing event is required. - Review special approvals or restrictions applying to certain purchases. |  | Issuing Officer
NI7 | Create Project Plan if an RFX is needed. Include dates and resources. |  | Issuing Officer |  |  |  | Draft Project Plan
PS1 | Determine if a consultant is needed. If consultant is used, the consultant must submit a nondisclosure and will be prohibited from participating in the sourcing event, unless SPD waives the restriction |  | Issuing Officer
PS2 | Identify and finalize the Cross-Functional and Evaluation Committee team members from procurement and key agency departments/divisions. Identify all end users, subject-matter experts, stakeholders. |  | Issuing Officer and End User(s) |  |  |  | List of Cross-Functional and Evaluation Committee members
PS3 | Plan and schedule a meeting with Cross-Functional Team Evaluation Committee members. - If conducting an RFP, use the SPD–EP023 RFP Evaluation Guidelines form to guide you through the process. |  | Issuing Officer |  |  |  | Date and Time for the meeting
PS4 | Conduct meeting with Cross-Functional Team - If conducting RFP, use the SPD–EP023 RFP Evaluation Guidelines form to guide you through the process - Have each member of the Cross-Functional team members execute conflict of interest form (Use the SPD–SP039 Evaluation Committee Member Participation form to obtain signatures) - Review team members roles and responsibilities and time commitments - Review the type of information needed and the format for the scope of procurement, scope of work, requirements, cost sheets, etc. Use SPD approved templates - Based on dollar value and sourcing event type, seeking DPA approval or assistance from SPD as applicable |  | Issuing Officer |  |  |  | Signed SPD – SP039 Evaluation Committee Member Participation forms
PS5 | Adjust Project Plan using information from previous meetings and distribute Project Plan for review to Cross-Functional team |  | Issuing Officer |  |  |  | - Draft Project Plan - Deadline for review
PS6 | Update Project Plan based on feedback from cross-functional team |  | Issuing Officer |  |  |  | Updated Project Plan
PS7 | Collect spend data and supplier information from: · Market · Agency · Federal Government and Other State Governments - Review current practices, spend data, and Ts and Cs from suppliers with whom the agency has done business. Whenever possible, collect a minimum of 12-months of data. - Review existing solicitations from agency, state, or other states - Seek input from existing contacts (end user, subject matter experts, suppliers, other agencies and states) - Identify the supplier pool (keep pools as broad and diverse as possible) - Collect supplier requirement info/understand market dynamics - Identify purchasing card acceptance opportunities based on market analysis - Review supplier/market portfolio with stakeholders - Address market and budget constraints; update estimated budget |  | Issuing Officer and End User |  |  |  | - Spend data analysis - List of possible suppliers
PS8 | Conduct an RFI, if needed. Use form SPD-PS013 State Entity eRFI Template.
PS9 | Determine if sole source or sole brand is needed. - Use SPD-PS019 Sole-Brand Justification Form to document justification and publish completed form with RFx posting. - If sole source applicable, use SPD-PS020 Sole-Source Intent to Award Justification as internal working document and complete data fields within GPR prior to posting.
PS10 | Address Delegated purchasing Authority requirements. If dollar amount exceeds entity's DPA then, SPD must approve. Use SPD's online Request to Exceed Delegated Purchasing Authority. | [5 empty] | If necessary, submitted DPA request form
PS11 | Plan and conduct a meeting with Cross-Functional/Evaluation team to review the market profile presentation. Review findings and determine sourcing strategy to follow (if any) (RFI, RFQ, RFQC, RFP). The RFP process may only be used as a method of solicitation after a written determination has been made that the use of competitive sealed bidding (RFQ) will not be practical or advantageous to the state entity. |  | Issuing Officer
PS12 | Update Project Plan and distribute to Cross-Functional team. Review Project Plan template in order to include additional tasks, assign additional resources, update completed tasks, ensure your due dates are still appropriate. |  | Issuing Officer |  |  |  | Updated project plan
SP1 | Draft RFx scope of procurement and scope of work. The purpose is to provide a high-level overview. Be clear and concise. |  | Issuing Officer and End User(s)
SP2 | Create the RFX Requirements and Questions - Define major categories - Define percentage to allocate to major categories - Develop questions/requirements for each major category - If conducting RFP or scored RFQC, define the points to assign to each individual question - Repeat the process above (develop questions for each major category, and assign points to each question as needed until you complete the requirements) - Use form SPD-SP057 - Requirements Sheet as a guide to complete this step. |  | Issuing Officer and Cross-Functional team |  |  |  | Completed Requirements Spreadsheet
SP3 | Plan and schedule a meeting to review requirements with cross-functional team. Review RFX requirements. |  | Issuing Officer
SP4 | Update Requirements based on feedback from review meeting |  | Issuing Officer |  |  |  | Finalized requirements spreadsheet
SP5 | If conducting an RFP (or scored RFQC), conduct a test-run to confirm that the proposal factors, percentages, and points are appropriate for RFP objectives. |  | Issuing Officer and cross-functional team
SP6 | Finalize RFX requirements based on feedback from test-run exercise and finalize worksheets (Mandatory, Mandatory Scored, and Additional Scored as applicable) |  | Issuing Officer |  |  |  | - Finalized RFP Requirements - Mandatory, Mandatory Scored, Additional Scored worksheets
SP7 | Define cost structure, format and methodology and create the cost line or cost worksheet |  | Issuing Officer and Cross-Functional team |  |  |  | Cost structure, cost line items and, if applicable, draft cost worksheet
SP8 | Plan and schedule a meeting to review cost structure information with cross-functional team |  | Issuing Officer
SP9 | Update cost structure and documentation based on feedback from review meeting |  | Issuing Officer |  |  |  | Updated Cost Sheet(s)
SP10 | Conduct a test-run to ensure cost proposal factors and formulas work correctly |  | Issuing Officer
SP11 | Finalize structure, cost line items, cost sheet(s) based on feedback from test-run exercise |  | Issuing Officer |  |  |  | Finalized Cost Sheet(s)
SP12 | For the draft RFX solicitation template, create schedule of events for the solicitation using the RFP Project Plan |  | Issuing Officer |  |  |  | Completed Schedule of Events
SP13 | Setup schedules and appointments with cross-functional and evaluation teams based on schedule of events |  | Issuing Officer |  |  |  | Appointments setup for each member
SP14 | Secure space for Offeror's conference(s), site visits, and evaluation meetings |  | Issuing Officer or assigned resource |  |  |  | Locations secured
SP15 | Create a definition of terms specific to the RFx for reference by suppliers. Include terminology used in the RFx that needs to be explained or defined. |  | Issuing Officer & Cross Functional Team |  |  |  | Definition of Terms document
SP16 | Review the insurance and bonds guidelines document to ensure proper insurance and/or bonds are included in the solicitation. Review SPD-SP048 Insurance and Bonding Guidelines as an informational resource. |  | Issuing Officer |  |  |  | Insurance and bonding requirements for RFx
SP17 | Assemble all necessary documents required in the solicitation. Review GPM Stage 3 for a list of applicable forms and templates. Access the library within SPD's Sourcing tool. |  | Issuing Officer
SP18 | Populate the Microsoft Word RFX Template |  | Issuing Officer |  |  |  | Completed RFx template and attachments
SP19 | Have the cross-functional team review the final copy of the RFx template and additional attachments |  | Cross-Functional team
SP20 | Update RFP based on feedback |  | Issuing Officer |  |  |  | Updated RFP
SP21 | If conducting RFP, complete RFP Preparation Scorecard by scoring the solicitation and submit to APO/CUPO. Use form SPD-SP051 RFP Preparation Scorecard. Copy should be saved with RFP working documents. |  | Issuing Officer |  |  |  | Completed RFP Preparation Scorecard
SP22 | Review RFP Preparation Scorecard and determine action plans needed |  | APO/CUPO
SP23 | Work through the action plan(s) included in the RFP Preparation Scorecard |  | APO/CUPO and Issuing Officer |  |  |  | Completed Action Plans
SP24 | Update RFP Requirements based on RFP Preparation Scorecard outcomes |  | Issuing Officer and Cross-Functional team
SP25 | Update and distribute project plan to cross-functional team |  | Issuing Officer |  |  |  | Updated Project Plan
SP26 | Create an evaluation tools (build evaluation framework). - Use form SPD-EP001 – Administrative Review Requirements Summary Sheet to create the Administrative Review evaluation tool |  | Issuing Officer |  |  |  | Evaluation Tool
SP27 | Gather and organize all correspondence, files, and supporting materials in a central location approved by your organization. Prior to posting the solicitation, coordinate with your records custodian regarding procurement and location of records in the event an Open Records Request is received. The issuing officer will continue to document and organize all records throughout the procurement. | [5 empty] | Centralized location for records
SPR1 | Post the solicitation in SPD's approved Sourcing tool. |  | Issuing Officer |  |  |  | Published solicitation.
SPR2 | If applicable, post Offeror's conference notification. - Use form SPD-SPR010 – Offeror's Conference Announcement template form to announce the Offeror's Conference. As a best practice, include this information as part of drafting the solicitation so it is included at the time of posting. |  | Issuing Officer
SPR3 | Secure court reporter for in-person Offeror’s conference (If applicable and check SWC for a court reporter). If conducting virtual meeting, record meeting. |  | Issuing Officer
SPR4 | Receive supplier written questions via Sourcing tool's Q&A Board. |  | Issuing Officer
SPR5 | Prepare responses to procurement questions and forward technical questions to Technical Lead for distribution to appropriate members. |  | Cross-Functional team
SPR6 | Schedule and conduct meeting to review written questions and answers with cross-functional team in order to document responses to written questions from suppliers. Use form SPD-SPR004 Supplier Q&A Template to document responses. |  | Issuing Officer
SPR7 | Post responses to written questions using Q&A Dashboard. Issuing officer may post individual responses to each question or post consolidated responses using SPD-SPR004 Supplier Q&A template. Responses may be published in "rounds". |  | Issuing Officer
SPR8 | Determine who, from the cross-functional team, will attend the offerors conference. |  | Issuing Officer and Cross-Functional team |  |  |  | List of attendees
SPR9 | Plan and schedule a meeting to review conduct, roles and responsibilities of members when attending offerors conference |  | Issuing Officer |  |  |  | - Meeting date, time and location - List of attendees with roles and responsibilities
SPR10 | Develop Offerors Conference Agenda and prepare a sign-in sheet for the meeting (in in person), and copy any handouts that will be distributed during the offeror’s conference. Use form SPD-SPR001 Bidders/Offerors Conference Agenda. |  | Issuing Officer |  |  |  | Offerors' Conference Agenda
SPR11 | Host the Offeror’s Conference. - Use form SPD-SPR007 Bidders/Offerors Conference Sign-In Form (as applicable) or use "chat"/attendee report from virtual meeting, and SPD-SPR001 Bidders/Offerors Conference Agenda - Have offerors sign-in |  | Issuing Officer and selected Cross-Functional team members
SPR12 | Document offeror's conference discussions and questions and ensure to include list of unanswered questions |  | Issuing Officer or designee
SPR13 | Provide answers to unanswered questions |  | Issuing Officer and Cross-Functional team
SPR14 | Post transcript and questions and answers from the Offeror’s Conference. For virtual offerors' conference, publish link to meeting recording. |  | Issuing Officer
SPR15 | Based on responses to supplier questions, identify any material changes that would require an addenda |  | Issuing Officer and Cross-Functional team |  |  |  | List of changes to RFX
SPR16 | If necessary, plan and conduct a meeting to modify the RFX (addenda) |  | Issuing Officer
SPR17 | If necessary, post addenda and additional information. Use form SPD-SPR013 RFX Addendum Form. |  | Issuing Officer |  |  |  | Published addenda.
SPR18 | Update RFP Project Plan and distribute to Cross-Functional team. Review RFP Project Plan template in order to include additional tasks, assigning additional resources, update completed tasks, ensure your due dates are still appropriate, |  | Issuing Officer |  |  |  | Updated project plan.
SPR19 | Receive Suppliers Responses via SPD's Sourcing tool.
EP1 | Complete Administrative Review of supplier responses. Use form SPD-EP001 – Administrative Requirements Summary Sheet to determine if the supplier is responsive, responsible and to identify if they have passed the Administrative Review. |  | Issuing Officer |  |  |  | Administrative review finalized
EP2 | For RFPs and Scored RFQCs only: In Sourcing tool, set up Panel Questionnaire and select suppliers to be included for technical scoring. |  | Issuing Officer
EP3 | Conduct Evaluation kick off meeting. - Inform Evaluation Committee members of the suppliers who passed the Administrative review - Obtain a signed copy of SPD-SP039 Evaluation Committee Member Participation Form. Determine if any members have a conflict of interest. - Review the evaluation guidelines, how to use the Sourcing tool's Panel Questionnaire to record ratings and comments, responsibilities, deadlines, and how to submit the evaluations once completed - Ensure the evaluation committee members understand that there is no communications with suppliers except through the Issuing Officer. |  | Issuing Officer
EP4 | Release the Panel Questionnaire via the Sourcing tool and set a deadline for finalizing the Supplier Technical Evaluation |  | Issuing Officer
EP5 | Plan and schedule the Validation meetings. The purpose of this meeting is to review and discuss the technical evaluations and provide SME presentations (if applicable or necessary) - Use and distribute out SPD-EP004 Evaluation Committee Agenda - Distribute SPD-EP023 Evaluation Committee Guidelines to the evaluation committee members |  | Issuing Officer
EP6 | If necessary, obtain any additional clarification from suppliers. Use form SPD-EP010 Request for Clarification. |  | Issuing Officer |  |  |  | Written clarifications
EP7 | If applicable, develop Offeror's demonstration instructions and/or oral presentations |  | Issuing Officer |  |  |  | Offeror's demonstration instructions
EP8 | If applicable, schedule and conduct Offeror demonstrations and/or oral presentations |  | Issuing Officer
EP9 | Complete technical evaluation scoring based on clarification, demonstrations and/or oral presentations |  | Evaluation Committee team members
EP10 | Conduct Validation meetings. The purpose of this meeting is to review each individual score and discuss the reason for the score. In addition, each member of the Evaluation Committee Team can change his/her score and provide a reason for the change. |  | Issuing Officer and Evaluation Committee members
EP11 | Complete Technical Evaluation. - Re-open the Panel Questionnaire to allow evaluation team members to adjust ratings and update comments, as desired. - Once all validation meetings are completed, re-close the Panel Questionnaire |  | Issuing Officer and Evaluation Committee team members |  |  |  | Updated technical evaluations following validation meetings.
EP12 | Conduct Price Proposal Reviews, Clarifications and Analysis. The Issuing Officer can do this in parallel of the Technical Review by the Evaluation Committee. |  | - Issuing Officer - If SPD, Strategic Support and Issuing Officer |  |  |  | Completed cost scoring
EP13 | Combine Technical and Cost scores (review in Sourcing tool) |  | Issuing Officer |  |  |  | Combined technical and cost scores
EP14 | Determine competitive range/top ranked and if negotiations are required. RFQs are limited to one round cost negotiation only. RFPs may include multiple rounds of technical and cost negotiations; however, issuing officer must have completed SPD negotiation certification. No negotiations are permitted on RFQCs. |  | Issuing Officer and Evaluation Committee team members |  |  |  | Graphic to support Competitive Range
EP15 | Determine negotiation team members |  | Issuing Officer and Cross-Functional team
EP16 | If negotiation is not being conducted, submit highest ranked supplier(s) contract exceptions (if any) to Legal for review. Submit agreement exceptions to legal support at your state entity. If legal support is not available within your state entity, contact the AG's office. |  | Issuing Officer
EP17 | Update Project Plan and distribute to Cross-Functional team. Review Project Plan in order to include additional tasks, assign additional resources, update completed tasks, ensure your due dates are still appropriate |  | Issuing Officer |  |  |  | Updated RFP Project Plan
EP18 | For RFPs, if negotiations are required and assistance is needed, please contact SPD and schedule a meeting to plan negotiation rounds. Use SPD approved negotiation templates (available to students completing SPD negotiation certification). Allow 5 to 10 days for notification. |  | Issuing Officer/SPD
EP19 | Prepare draft negotiation documents |  | Issuing Officer/SPD
EP20 | Plan and conduct negotiation team kick-off and strategy meeting. Review SPD-EP018 Negotiations Workbook and reconfirm Key Objectives, SWOT Analysis and Vision Statement. Review and prepare SPD-EP017 Negotiations Script. |  | Issuing Officer/SPD
EP21 | Invite offerors to negotiation meetings. Use SPD-EP016 Invitation to Negotiations and share Meeting Agenda. Allow 5 to 10 days for notification. |  | Issuing Officer/SPD
EP22 | Conduct negotiation(s)/discussions. Reference GPM as applicable or SPD regarding permitted scope of negotiations. |  | Issuing Officer, SPD, and Negotiations Team
EP23 | Following negotiation discussions, instruct suppliers to resubmit revised responses. Use "Stage" feature in Sourcing tool for RFQ cost negotiation or RFP cost negotiation. For RFP technical negotiations, direct suppliers to submit the revised responses to the Issuing Officer via email. |  | Issuing Officer/SPD
EP24 | Submit revised worksheets to Evaluation Committee members for scoring |  | Issuing Officer/SPD
EP25 | Receive and tally their scores |  | Issuing Officer/SPD
EP26 | Conduct Validation meeting |  | Issuing Officer, SPD, and Evaluation Team
EP27 | Conduct negotiation of contractual terms. Invite Legal. |  | Issuing Officer and Legal
EP28 | Complete evaluation |  | Issuing Officer |  |  |  | Evaluation completed
EP29 | Submit Sales Compliance Tax form to DOR for approval. Use form SPD-SP045 Tax Compliance and confirm that recommend offeror is in compliance. |  | Issuing Officer
EP30 | If necessary, receive executive approval to execute contract |  | Issuing Officer
EP31 | Receive approval from DOR on supplier status. If status is not in compliance, provide the supplier the opportunity to fix issue with DOR. Set a finite number of days for resolution. If there is no resolution, move on to the next highest ranked supplier. |  | Issuing Officer
EP32 | Assemble all Sourcing documents and catalog them electronically. Documents include the actual RFP, responses and attachments from each supplier, scoring sheets, communication logs, emails related to the solicitation, posted responses to questions, negotiation points, documentation from the negotiation meeting(s), etc. |  | Issuing Officer |  |  |  | File containing RFP documentation
EP33 | Obtain supplier's signature on contract. The state entity's signature will be completed after the supplier signs the contract. |  | Issuing Officer
AP1 | If applicable, post NOIA. Use form SPD-AP004 Notice of Intent to Award (NOIA). |  | Issuing Officer |  |  |  | Published NOIA
AP2 | If a protest is filed, post protest information as directed by SPD. See GPM Section 6.5 for general information. |  | Issuing Officer
AP3 | Stay procurement award (and do not execute contract) until SPD protest process completed or as otherwise directed by SPD. |  | Issuing Officer and SPD Legal
AP4 | SPD issues protest decision |  | SPD |  |  |  | Protest Decision
AP5 | Following protest decision, observe appeal filing period. If appeal filed, continue stay on procurement award until process completed. |  | Issuing Officer
AP6 | Once protest/appeal is completed (and subject to other directions in the protest/appeal decision), post NOA and notify Cross-Functional team of resolution. Use form SPD-AP005 Notice of Award (NOA). |  | Issuing Officer |  |  |  | Appeal Decision; Published Notice of Award
AP7 | Obtain all state entity's signatures on the contract, execute the contract, and issue a PO |  | Issuing Officer |  |  |  | Signed contract(s)
AP8 | Send copy of executed contract to selected supplier(s) |  | Issuing Officer
AP9 | Document lessons learned (recommended) for future procurements |  | Issuing Officer and Cross-Functional team |  |  |  | Lessons learned documented
AP10 | Receive request(s) for supplier debriefing from unsuccessful suppliers. Opportunity for unsuccessful suppliers to gain insight into the procurement process and be more competitive in future bids |  | Unsuccessful supplier initiates request; Issuing Officer to receive
AP11 | Acknowledge receipt of the request and notify the supplier of the scope; format and date, time, and place (if applicable). Review GPM for more information. |  | Issuing Officer
AP12 | Supplier acknowledges receipt; confirms intent to participate (if in person or by phone) and identifies who will attend |  | Supplier; Issuing Officer to receive
AP13 | Conduct Supplier Debriefing (in person, remotely, via phone call or in writing) |  | Issuing Officer |  |  |  | Agenda (if live event); supplier’s evaluation results (overall ranking and scores; or, if disqualified, the reason for disqualification)
AP14 | Place documentation of the supplier debriefing(s) conducted with the procurement files. Examples of materials to maintain includes: the supplier’s request, the state entity’s response and any other related correspondence, meeting agenda, list of individuals attending the meeting, any documents provided to the suppliers, notes taken during the meeting, etc. |  | Issuing Officer
CP1 | Conduct kick-off meeting with awarded supplier(s). Discuss Service Level Agreements and performance expectations. |  | Issuing Officer (if applicable), Agency Contract Administrator, Project Sponsor, etc.
CP2 | Create contract file and administration plan. Use SPD-CP016 Contract Administration Plan Template. |  | Contract Administrator
CP3 | Create a schedule for tracking contract performance and payments. Track performance throughout life of contract and conduct Quarterly/Semiannually Meetings. |  | Contract Administrator