## Sheet1
Agency Acronym | Agency | CAI POC | Transition Status | Date V2 Engagement List Sent | Date V2 Engagement List Returned (Complete) | # V2 Transition Engagements Identified | Status of Confirmed Engagements | Additional Transition Engagements Anticipated | Status of Anticipated Engagements | Notes | SOW | SOW Details (if available) | Compliance Items Captured? (if so, see next tab) | PO/Invoice Process Captured? (if so, see PO tab) | Agency/Rate Final Review Outreach | Agency Final Review Date | Rate Approval Received From Agency | Transition Complete | Transition Notes
[6 empty] | Shows total # of transition engagements recently reported by agency | Shows how many engagements from Column C where pay data/stubs have been validated and rate calculations are complete | In instances where the Agency has not yet returned their data, we did the exercise from Column C & D using the engagement lists collected back in May/June. (Note: Data is subject to change upon receiving updated data from each agency) | Shows how many of the total from Column E where pay data/stubs have been validated and rate calculations are complete
CJCC | Criminal Justice Coordinating Council |  | Complete- 10/1/19 Start | 2019-08-23 | 2019-08-26 | 2 | Transitions Complete | N/A | N/A | Yearly budget Savings $3,620 | All Completed | Per TS | Yes | Yes | 2019-09-25 | 2019-09-26 | 2019-09-26 | 2 of 2 | Transitions Complete
DBHDD | Dept. of Behavioral Health & Developmental Disabilities |  | Awaiting Transition dates from agency | 2019-08-27 | 2019-08-28 | 27 | 26 of 29 Complete | N/A | N/A | Finalization mtg complete 10/10. Doug to provide transition dates by early Nov. | 11 | See T. Simpson email from 10/4/19 @ 11:54 for details | Yes | Yes | 2019-10-08 | 2019-10-10 |  |  | Finalization mtg complete 10/10. Doug to provide transition dates by early Nov.
DCA | Department of Community Affairs | Tim | Transition date 11/1/19: Reqs released 10/23/19 | 2019-08-27 | 2019-09-18 | 2 | 2 of 2 Complete | N/A | N/A |  | 3 | DCA Website – UGA; DCA Application Support Deliverable – UGA; DCA Application Support - UGA |  |  | 2019-10-22 | 2019-10-23
DCH | GA Dept of Community Health | Susan | Contacting to set Transition Finalization Mtg | 2019-08-27 | 2019-08-29 | 10 | 8 of 10 Complete | N/A | N/A |  | None
DCS | GA Department of Community Supervision |  | Transition date 11/15/19: Awaiting Rate Finalization | 2019-08-27 | 2019-09-10 | 17 | 16 of 17 Complete | N/A | N/A | Contacted for finalization meeting 10/8 |  |  |  |  | 2019-10-08 | 2019-10-24
DDS | Ga. Dept. of Drivers Services |  | Transition date 12/1/19: Reqs released 10/14 | 8/23; 9/16; 10/1 | 2019-10-02 | 16 | 13 of 16 Complete | N/A | N/A | Contacted for finalization meeting 10/8. Mtg 10/10 |  |  | Yes | Yes | 2019-10-08 | 2019-10-10 |  |  | Transition Date 12/1/19: Reqs released
DECAL | Ga. Dept. of Early Care and Learning | Tim |  | 2019-08-27 | 2019-08-28 | 26 | 21 of 26 Complete | N/A | N/A |  | None
Dekalb | Dekalb County School District |  |  | 8/27 & 10/1 | 2019-10-10 | 19 | 11 of 19 Complete | N/A | N/A
DHS | Ga. Dept. of Human Services | Susan | Transition date 12/1/19: Awaiting Rate Finalization | 2019-09-03 | 2019-09-18 | 86 | 74 of 86 Complete | N/A | N/A | Working to set finalization meeting |  |  |  |  | 2019-10-08 | 2019-10-24 |  |  | Transition Date 12/1/19:
DJJ | Ga. Dept. of Juvenile Justice | Susan | TT TS before scheduling based on client parameters | 8/27 & 10/1 | 2019-10-10 | 21 | 19 of 21 Complete | N/A | N/A
DNR-EPD | Ga. Dept. of Natural Resources - Environmental Protection Division | Susan | Transition date 11/1/19: Reqs released 10/11/19 | 8/23/2019 & 9/27/19 | 2019-09-30 | 10 | 10 of 10 Complete | N/A | N/A | Transition reqs (except 1) released | 4 | Ag Permitting GIS Development (Matrix Resources); Database Migration (Equi-tek); Business Process Automation of Environment Review & Tax Incentive Programs (Equi-tek); Database Update and Migration (Equi-tek) | Yes | Yes | 2019-10-08 | 2019-10-10 | 2019-10-10 |  | Reqs released 10/11/19
DOAS | Dept. of Administrative Services | Tim | In Process following Daren direction | Data Provided Previously | N/A | 12 | (7 of 12 Already Engaged. 2 Team Informatics will not transition, 1 in process, last 2 around Dec) | N/A | N/A |  | 1 | Done | Yes | Yes | N/A | N/A | N/A
DOE | Ga. Dept. of Education | Tim | Transition date 10/1/19: Complete | Ongoing | N/A | 42 | Transition Complete (except for M. Lanka) | N/A | N/A |  |  |  | Yes | Yes | N/A | N/A | N/A
DOR | Ga. Dept. of Revenue/ITD | Susan |  | 2019-08-29 | 2019-09-18 | 48 | 40 of 48 Complete | N/A | N/A
DPH | GA Dept of Public Health | Susan | Transition date 12/1/19: Awaiting Rate Finalization | 2019-08-29 |  | 41 | 39 of 41 Complete | N/A | N/A |  |  |  | Yes | Yes | N/A | 2019-10-25 |  |  | Transition 12/1/19: Awaiting Mauri rate approval
Fulton Cty Govt | Fulton County Government | Susan | Transition Date 10/1/19: Complete | 2019-08-23 | 2019-09-16 | 1 | Transition Complete | N/A | N/A | Yearly budget savings $6,560 | 1 | PM (Slalom) | Yes | Yes | 9/24 & 9/26 | 2019-09-30 | 2019-09-30 |  | Transition req released 9/30
GA Tech- OIT | GA Tech- Office of Information Technology | Tim |  | 2019-08-29 | 2019-08-28 | 20 | 10 of 20 Complete | N/A | N/A |  | None***
GDC | Ga. Dept. of Corrections |  | Transition date 12/1. Still need stubs for several | 2019-08-29 |  | 36 | 28 of 36 Complete | N/A | N/A | [6 empty] | 2019-10-16 | 2019-10-16 |  | Transition 12/1, still need lot of stubs
GDOL | Ga. Dept. of Labor |  |  | 2019-08-29 | 2019-09-05 | 35 | 28 of 35 Complete | N/A | N/A
GDOT | Georgia Department of Transportation | Tim |  | 2019-09-10 |  |  |  | 105 | 87 of 105 | [9 empty] | Make note of Mgr per Tommy
GPSC | Ga. Public Service Commission | Susan | Transition date 1/1/20: Complete | 2019-08-23 | 2019-09-19 | 1 | Req Released 10/2- Transition 1/1/20 | N/A | N/A | Yearly budget increases $4,260 |  |  | Yes | Yes | 9/25 & 10/1 | 2019-10-02 | 2019-10-02 | Yes | Req released 10/2- Transition 1/1/20
GSFC | Georgia Student Finance Commission | Tim | Transition date 12/1/19: Reqs released 10/21 | 2019-08-23 | 2019-08-26 | 3 | 3 of 3 Complete | N/A | N/A | Yearly budget increases $3,300 | None |  |  |  | 2019-09-25 | 2019-09-27 |  |  | Transition 12/1/19
GSFIC-F&I | GSFIC-F&I (GA State Financing and Investment Commission) |  |  | 8/29; 9/17; 10/1 |  |  |  | 1 | 0 of 1 Complete | Steve Elmore have 2 Engagements w/ 2 agencies?
GSU | Georgia State University | Tim |  | 2019-08-29 | 2019-08-30 | 10 | 7 of 10 Complete | N/A | N/A
GTA | Georgia Technology Authority | Susan | Transition date 11/15/19: Reqs released 10/24/19 | 2019-08-29 | 2019-08-30 | 13 | 13 of 13 Complete | N/A | N/A | Contacted for finalization meeting 10/8 |  |  | Yes | Yes | 2019-10-08 | 2019-10-23 | 2019-10-23 |  | Transition Date: 11/15/19
GTRI | Georgia Tech Research Institute | Tim | Contacting to set Transition Finalization Mtg: Proposed Fri 10/25 @11:00 | 2019-08-27 | 2019-08-28 | 8 | 8 of 8 Complete | N/A | N/A |  | None
OPB | Governor's Office of Planning and Budget |  |  | 2019-08-29 | 2019-08-30 | 1 | 0 of 1 Complete | N/A | N/A | Steve Elmore have 2 Engagements w/ 2 agencies?
OSAH | Office of State Administrative Hearings |  |  | 2019-08-29 | 2019-09-04 | All SOW | N/A | N/A | N/A |  | 2
SAO | State Accounting Office |  |  | 2019-08-29 |  | 3 | Emd 10/10 to set transition finalization mtg | N/A | N/A | Kyle Morton switch to GDOT? | None |  |  |  | 2019-10-10
SBWC | State Board of Worker's Compensation |  | Contacting to get SRP contact info and Set Finalization Mtg | 8/29 & 9/17 |  |  |  | 6 | 4 of 6 Complete- Need 2 SRP contact info | Agency wants to wait until 12/2019 to transition
SOS | Office of Secretary of State | Tim |  | 2019-08-29 | 2019-09-10 | 4 | 3 of 4 Complete | N/A | N/A |  | 9
SRTA | State Road and Tollway Authority |  | They need to send details for 2 more transitions | 8/29 & 10/1 | 2019-10-04 | 1 | 1 of 1 Complete | N/A | N/A | Transition 1/1 per client
TCSG | Technical College System of Gerogia |  | Contacting to set Transition Finalization Mtg | 2019-08-29 | 2019-09-19 | 1 | 1 of 1 Complete- Pending Invoice | N/A | N/A | Need TSR invoice to validate pay rate
USG-BOR | USG - GA Board of Regents | Tim |  | 2019-08-23 | 2019-08-28 | 24 | 20 of 24 Complete | N/A | N/A |  | None
[5 empty] | Total: | 540 | Total: | 112 | [5 empty] | Total:
Transition Complete
KSU | Kennesaw State Univ |  |  |  | 0 to Transition | 0
DBF | Georgia Department of Banking & Finance |  |  | 2019-08-23 | 0 to Transition | 2 | 2 of 2 Complete |  |  | that since both contracts were created with prior years’ funds its best to continue with Covendis until the contracts are completed
GBI | GA Bureau of Investigation | Susan |  | 2019-08-28 | 0 to Transition | 0
[5 empty] | Total: | 2