## Sheet1
Task Name | Week(s) of
Inception
Project Kickoff | 2015-01-12
Requirements Gathering - Analysis and Design Discussions | 2015-01-19
Document review/research | 2015-01-19
Analysis and Design Document | 2015-01-26
Development/Construction
Enhancements to Extract utility for document extraction
Enhancements to XML Generation for metadata process
Installation
Establish Access to GDOAS Resources (VPN, iSeries, Remote Windows desktop)
Install extraction utility in GDOAS environment
Install XML Generation for metadata utility in GDOAS environment
Testing
Preparation
Create sample test data
GDOAS Location Testing
Test extracting documents in GDOAS environment to verify extaction functionality
Test XML Generation for metadata process in GDOAS environment
Test loading of the extracted documents in GDOAS environment to verify loading functionality
Implementation Support
Extration training to run processes
Support as needed for 10 hours to assist with extration of documents
Delta Migration and Audit / Reconcillation
Project Signoff